## Phase3-TeamPlanning2023
CSI4142 - Project 2023
Phase 4 - Data Mining
Teamwork - breakdown of duties
Group 41
Deliverable checklist | Responsible | Expected completion date | Actual completion date | Estimated | Actual | Notes (if any)
| team member(s) |  |  | time (hours) to complete | time (hours) to complete
Data preprocessing
Data summarisation | Hamza Israr/Aleana Wright | April 9th | April 9th |  | 2
.. Visualisation of attributes | Hamza Israr/Aleana Wright | April 9th | April 9th |  | 2
Data transformation |  | April 8th | April 9th | 1 | 3 | All data transformation steps done in the same 3 hour session
.. Missing values | Michael Quach | April 8th | April 9th | 1 | 3
.. Categorical data | Michael Quach | April 8th | April 9th | 1 | 3
.. Numeric data | Michael Quach | April 8th | April 9th | 1 | 3
.. Feature selection | Michael Quach | April 8th | April 9th | 1 | 3
Data mining - Classification
Decision tree | Not required by TA
Gradient Boosting | Not required by TA
Random Forests | Not required by TA
Comparison of results | Not required by TA
Summary | Not required by TA
Anomaly detection
One-class SVM | Bonus | April 9th | Not done
Summary | Bonus | April 9th | Not done
Other tasks - please specify
Phase 4 PDF | Michael Quach | April 9th | April 9th | 1 hour | 30 minutes